## Test Cases
Aut Test ID | Flow | Status | Owner | Start Date | Planned End Date | Actual End Date
NB_ModProg_AddintionalInsured Add | "NB > Basic Program > Additional Insured Add | InProgress | Akula Srikanth | 2021-03-31 | 2021-04-03 |  | PC_AUT_01
AUT_TS_02 | "NB > Standard Program > Organization Mod> Affinity Goup Addition>Primary Named Insured Mod>Address Add>UW Company Mod>Coverages Del>Prior policies Mod>Prior policies Del>Schedule" | InProgress | Gautham Karanam | 2021-03-31 | 2021-04-03
AUT_TS_03 | NB > Standard Program > Organization Mod > Additional Insured Add > Additional Insured Mod > Primary Named Insured Mod>Address Mod>Policy Info Mod> Driver Info Add > Driver Info Mod>Vehicle Info Add>Coverages Mod>Prior losses entry>Prior losses Mode>Prior losses Del> Quote > UW Issues approval > Payment > Issue | InProgress | Akash Gowda | 2021-03-31 | 2021-04-03
AUT_TS_04 | NB > Premium Program > Additional Insured Add > Additional Insured Del > Secondary Named Insured Add > UW Company Mod > Driver Info Add > Vehicle Info Add > Coverages Modification > Prior policies Entry > Billing Type 1 > 6 months schedule > Premium match | InProgress | Shweta Yaradoni | 2021-03-31 | 2021-04-03
AUT_TS_05 | > Secondary Named Insured Add > UW Company Mod > Driver Info Add > Vehicle Info Add > Coverages Modification > Prior policies Entry > Billing Type 1 > 6 months schedule > Premium match>Policy Details Review>Forms trigger and ordering validation>Billing type > PC > Secondary Named Insured Del" | Yet2Start
AUT_TS_06 |  | Yet2Start
AUT_TS_07 |  | Yet2Start
AUT_TS_08 |  | Yet2Start
AUT_TS_09 |  | Yet2Start
AUT_TS_10 |  | Yet2Start
AUT_TS_11 |  | Yet2Start
AUT_TS_12 |  | Yet2Start
AUT_TS_13 |  | Yet2Start
AUT_TS_14 |  | Yet2Start
AUT_TS_15 |  | Yet2Start
AUT_TS_16 |  | Yet2Start
AUT_TS_17 |  | Yet2Start
AUT_TS_18 |  | Yet2Start
AUT_TS_19 |  | Yet2Start
AUT_TS_20 |  | Yet2Start
AUT_TS_21 |  | Yet2Start
AUT_TS_22 |  | Yet2Start
AUT_TS_23 |  | Yet2Start
AUT_TS_24 |  | Yet2Start
AUT_TS_25 |  | Yet2Start
AUT_TS_26 |  | Yet2Start
AUT_TS_27 |  | Yet2Start
AUT_TS_28 |  | Yet2Start
AUT_TS_29 |  | Yet2Start
AUT_TS_30 |  | Yet2Start
AUT_TS_31 |  | Yet2Start
AUT_TS_32 |  | Yet2Start
AUT_TS_33 |  | Yet2Start
AUT_TS_34 |  | Yet2Start
AUT_TS_35 |  | Yet2Start
AUT_TS_36 |  | Yet2Start
AUT_TS_37 |  | Yet2Start
AUT_TS_38 |  | Yet2Start
AUT_TS_39 |  | Yet2Start
AUT_TS_40 |  | Yet2Start
AUT_TS_41 |  | Yet2Start
AUT_TS_42 |  | Yet2Start
AUT_TS_43 |  | Yet2Start
AUT_TS_44 |  | Yet2Start
AUT_TS_45 |  | Yet2Start
AUT_TS_46 |  | Yet2Start
AUT_TS_47 |  | Yet2Start
AUT_TS_48 |  | Yet2Start
AUT_TS_49 |  | Yet2Start
AUT_TS_50 |  | Yet2Start
AUT_TS_51 |  | Yet2Start
AUT_TS_52 |  | Yet2Start
AUT_TS_53 |  | Yet2Start
AUT_TS_54 |  | Yet2Start
AUT_TS_55 |  | Yet2Start
AUT_TS_56 |  | Yet2Start
AUT_TS_57 |  | Yet2Start
AUT_TS_58 |  | Yet2Start
AUT_TS_59 |  | Yet2Start
AUT_TS_60 |  | Yet2Start
AUT_TS_61 |  | Yet2Start
AUT_TS_62 |  | Yet2Start
AUT_TS_63 |  | Yet2Start
AUT_TS_64 |  | Yet2Start
AUT_TS_65 |  | Yet2Start
AUT_TS_66 |  | Yet2Start
AUT_TS_67 |  | Yet2Start
AUT_TS_68 |  | Yet2Start
AUT_TS_69 |  | Yet2Start
AUT_TS_70 |  | Yet2Start
AUT_TS_71 |  | Yet2Start
AUT_TS_72 |  | Yet2Start
AUT_TS_73 |  | Yet2Start
AUT_TS_74 |  | Yet2Start
AUT_TS_75 |  | Yet2Start
AUT_TS_76 |  | Yet2Start
AUT_TS_77 |  | Yet2Start
AUT_TS_78 |  | Yet2Start
AUT_TS_79 |  | Yet2Start
AUT_TS_80 |  | Yet2Start
AUT_TS_81 |  | Yet2Start
AUT_TS_82 |  | Yet2Start
AUT_TS_83 |  | Yet2Start
AUT_TS_84 |  | Yet2Start
AUT_TS_85 |  | Yet2Start
AUT_TS_86 |  | Yet2Start
AUT_TS_87 |  | Yet2Start
AUT_TS_88 |  | Yet2Start
AUT_TS_89 |  | Yet2Start
AUT_TS_90 |  | Yet2Start
AUT_TS_91 |  | Yet2Start
AUT_TS_92 |  | Yet2Start
AUT_TS_93 |  | Yet2Start
AUT_TS_94 |  | Yet2Start
AUT_TS_95 |  | Yet2Start
AUT_TS_96 |  | Yet2Start
AUT_TS_97 |  | Yet2Start
AUT_TS_98 |  | Yet2Start
AUT_TS_99 |  | Yet2Start
AUT_TS_100 |  | Yet2Start
AUT_TS_101 |  | Yet2Start
AUT_TS_102 |  | Yet2Start
AUT_TS_103 |  | Yet2Start
AUT_TS_104 |  | Yet2Start
AUT_TS_105 |  | Yet2Start
AUT_TS_106 |  | Yet2Start
AUT_TS_107 |  | Yet2Start
AUT_TS_108 |  | Yet2Start
AUT_TS_109 |  | Yet2Start
AUT_TS_110 |  | Yet2Start
AUT_TS_111 |  | Yet2Start
AUT_TS_112 |  | Yet2Start
AUT_TS_113 |  | Yet2Start
AUT_TS_114 |  | Yet2Start
AUT_TS_115 |  | Yet2Start
AUT_TS_116 |  | Yet2Start
AUT_TS_117 |  | Yet2Start
AUT_TS_118 |  | Yet2Start

## Coverage
Transaction | Screens | Functionalities
New Business | Offerings | Basic Program
Standard Program
Premium Program
| Policy Info | Additional Insured Add
Additional Insured Del
Additional Insured Mod
Secondary Named Insured Add
Secondary Named Insured Del
Secondary Named Insured Mod
Organization Mod
Affinity Goup Addition
Primary Named Insured Mod
Address Add
Address Mod
Policy Info Mod
UW Company Mod
| Drivers | Driver Info Add
Driver Info Del
Driver Info Mod
| Vehicles | Vehicle Info Add
Vehicle Info Del
Vehicle Info Mod
| Coverages | Coverages Add
Coverages Del
Coverages Mod
| Risk Analysis | Prior policies entry
Prior policies Mod
Prior policies Del
Prior losses entry
Prior losses Mod
Prior losses Del
UW Issues approval
| Policy Review | Policy Details Review
| Forms | Forms trigger and ordering validation
| Billing | Billing type
Schedule
Premium
Change | Offerings | Basic Program
| Policy Info | Additional Insured Add
Additional Insured Del
Additional Insured Mod
Secondary Named Insured Add
Secondary Named Insured Del
Secondary Named Insured Mod
Organization Mod
Affinity Goup Addition
Primary Named Insured Mod
Address Add
Address Mod
Policy Info Mod
UW Company Mod
| Drivers | Driver Info Add
Driver Info Del
Driver Info Mod
| Vehicles | Vehicle Info Add
Vehicle Info Del
Vehicle Info Mod
| Coverages | Coverages Add
Coverages Del
Coverages Mod
| Risk Analysis | Prior policies entry
Prior policies Mod
Prior policies Del
Prior losses entry
Prior losses Mod
Prior losses Del
UW Issues approval
| Policy Review | Policy Details Review
| Forms | Forms trigger and ordering validation
| Billing | Billing type
Schedule
Premium
Cancellation | Cancellation Confirmation screen | Mid Term Cancellation
New Business Cancellation
Insured Cancellation
Insurer Cancellation
Reinstate | Start Reinstatement | Reinstatement Reason
| Risk Analysis | Prior policies entry
Prior policies Mod
Prior policies Del
Prior losses entry
Prior losses Mod
Prior losses Del
UW Issues approval
Rewrite | Offerings | Change Program
| Policy Info | Additional Insured Add
Additional Insured Del
Additional Insured Mod
Secondary Named Insured Add
Secondary Named Insured Del
Secondary Named Insured Mod
Organization Mod
Affinity Goup Addition
Primary Named Insured Mod
Address Add
Address Mod
Policy Info Mod
UW Company Mod
| Drivers | Driver Info Add
Driver Info Del
Driver Info Mod
| Vehicles | Vehicle Info Add
Vehicle Info Del
Vehicle Info Mod
| Coverages | Coverages Add
Coverages Del
Coverages Mod
| Risk Analysis | Prior policies entry
Prior policies Mod
Prior policies Del
Prior losses entry
Prior losses Mod
Prior losses Del
UW Issues approval
| Policy Review | Policy Details Review
| Forms | Forms trigger and ordering validation
| Billing | Billing type
Schedule

## Login
PrimaryKey | TD_UserName | TD_Password
SuperUser | su | gw
User1 | susa | pad
User2 | stuart | art
User3 | midas | lat
User4 | enrich | net
User5 | alex | lin
User6 | mabo | dhu
User7 | tallen | gw

## AccountCreation
PrimaryKey | Account No | Name | First name | Last name | Office Phone | Fax | Home Phone | Work Phone | Mobile Phone | Fax Phone | Primary Phone | Primary Email | Secondary Email | Country | Address 1 | Address 2 | Address 3 | City | County | State | ZIP Code | Address | Type
BillPlan1 | Insured | QA1BILLINGPLAN01 | Equity-Based Delinquency Plan | Email | Wright Construction
BillPlan2
BillPlan3
BillPlan4
BillPlan5

## Policy
PrimaryKey | TD_BillingMethod | TD_PaymentPlan | TD_CompanyName | TD_ChargesType | TD_ChargesAmount
PaymentPlan1 | Direct Bill | B Monthly 10% Down, Max 11 installments | Wright Construction | Premium | 1000
PaymentPlan2
PaymentPlan3
PaymentPlan4
PaymentPlan5

## AcctSummary
PrimaryKey | TD_AccountName | TD_PayoffAmount | TD_PolicyNumber | TD_TotalValue
AcctSumry1 |  | $1,000.00 |  | $1,000.00
AcctSumry2
AcctSumry3
AcctSumry4
AcctSumry5